General Timeline Tips

This list is tailored for managing large, complex proposals. This template synthesizes best practices and is designed to be adaptable across various funders—federal, foundation, non-profit, and industry—and can be customized based on specific sponsor requirements or institutional workflows. This checklist is a general guide. Specific timelines and requirements may vary based on the sponsor and institutional policies. Always consult with your research administration office for tailored guidance.

6-12 Months Before Deadline

- Identify Funding Opportunity

  - Review solicitations (RFP, FOA, NOFO) thoroughly.

  - Confirm eligibility and alignment with institutional priorities.

- Engage Stakeholders

  - Notify department chairs, deans, and research administration of intent to submit.

  - Initiate contact with potential collaborators and subawardees.

- Preliminary Planning

  - Schedule a kickoff meeting with the research development team.

  - Develop a high-level project outline and objectives.

- Compliance and Training

- Ensure all team members have up-to-date certifications (e.g., CITI training).

- Begin IRB/IACUC protocols if human or animal subjects are involved.

- Start early on any agency-specific compliance requirements. For example, DOE requires security training to be completed at least 12 months prior to proposal submission—some requirements may take significant lead time.

3-6 Months Before Deadline

- Project Development

  - Define specific aims, research strategy, and methodologies.

  - Assign roles and responsibilities among team members.

- Budget Planning

  - Draft preliminary budget and justification.

  - Identify cost-sharing or matching fund requirements.

2-3 Months Before Deadline

- Document Preparation

  - Compile biosketches, current and pending support, and facilities/resources documents.

  - Request letters of support or collaboration.

- Internal Review

  - Submit draft proposal components for internal peer review.

  - Incorporate feedback and revise accordingly.

- Administrative Coordination

  - Coordinate with subaward institutions to gather necessary documents.

  - Begin routing internal approval forms as per institutional policies.

1 Month Before Deadline

- Finalize Proposal Components

  - Complete all narrative sections, ensuring alignment with sponsor guidelines.

  - Finalize budget and justification with institutional grants office.

- Compliance Checks

  - Verify all compliance documents are in place.

  - Confirm all institutional approvals have been obtained.

2 Weeks Before Deadline

- Submission Preparation

  - Upload all components into the sponsor's submission portal.

  - Conduct a thorough review for formatting, page limits, and required attachments.

- Final Review

  - Share the complete proposal package with the research administration office for final review.

1 Week Before Deadline

- Address Feedback

  - Respond to any comments or required changes from the research administration office.

  - Ensure all final materials are submitted to RSP at least 5 business days prior to the sponsor deadline, in accordance with UW–Madison policy.