## Gantt Timeline
Who | What | Status | Start Date | End Date | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10
Early Priority Tasks
SRH Proposal Development Coordinator | Attend webinar, read call | Complete | 2026-09-10 | 2026-10-10
SRH Proposal Development Coordinator | Create and share timeline and checklist and project folder | In Progress | 2026-09-10 | 2026-10-10
SRH Proposal Development Coordinator | Confirm research security training completion and if not notify they will need to complete it | Not Started | 2026-09-10 | 2026-10-10
SRH Proposal Development Coordinator | Kickoff followup email and any necessary links for personnel docs, NSPIRES registeration, etc. | Not Started | 2026-09-10 | 2026-10-10
Full Proposal Tasks
PI | Initiate Full Proposal in NSPIRES and add your research adminstrator | Not Started | 2026-09-10 | 2026-10-10
SRH Grant Writer | Research Team and James coordinate on proposal section writing needs | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Research Admin coordinate with Research Team leads on budget and justification | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Initiate RAMP record | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Coordinate with PI to certify RAMP record | Not Started | 2026-09-10 | 2026-10-10
SRH Proposal Development Coordinator | Reachout to any subwards and any internal department RA's to coodinate budget and personnel doc pieces | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Deadline for requested materials from external collborators (budget, budget justification, SOW, Letter of Intent, Letters, C&P, biosketch, table of effort, facilities and eqipment (if applicable for the project). Note NASA will only accept biosketch and C&P using SciENcv as of Sept 1, 2026 | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Enter budget into RAMP | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Upload budget docs into RAMP | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Request RAMP ancillary reviews | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Enter budget into NSPIRES | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Request RAMP division review | Not Started | 2026-09-10 | 2026-10-10
Final Routing and Submission Tasks
Division Research Administrator | Division routes RAMP record to RSP | Not Started | 2026-09-10 | 2026-10-10
Dept Research Administrator | Once division routes RAMP to RSP, PI must grant AOR access in NSPIRES to offically submit proposal (note, PI cannot be the one to push the submit button, it MUST be the AOR who does that) | Not Started | 2026-09-10 | 2026-10-10
10/15/2026 11:59 PM EST | SPONSOR DUE DATE | Not Started | 2026-09-10 | 2026-10-10

## Checklist
Title:
Lead PI: |  |  |  |  | RAMP FP:
Project Dates: |  |  |  |  | Deadline:
Solicitation #: |  |  |  |  | Budget:
Temporary ID #: |  |  |  |  | Award Type:
NASA Formatting Guidelines
Page and Text Formatting: 8.5" x 11.0" page size, single spaced, single column text (unless otherwise specified). One-inch margins on all four sides. No reviewable content in margins. No more than 5.5 lines per vertical inch. No more than 15 characters per horizontal inch, including spaces. This is typically consistent with a font size of 12.
Reference callouts in the proposal text must be in numerical format (e.g. [1], [2], etc.). It is recommended that the callouts appear in numerical order in the text
Captions Formatting: As above (font size 12 etc.). Text necessary for the proposal may not be solely in figures, tables, or their captions.
Figure Formatting: Text and content on/in figures must be easily legible without magnification.
Table Formatting: Text and content on/in Tables must be easily legible without magnification.
Proposal Package Parts & Content | Lead | Working Draft Due Date | Final Draft Due Date (internal) | Status | Pages | Hyperlink to template or working document | Notes
Part 1: NSPIRES Cover Page | Holly |  |  | Not Started | NA
Part 2: Anonymized Proposal Document must contain the following sections in the following order:
Science-Technical-Management (S/T/M; 10pp) |  |  |  | Not Started | 10 pg limit
References |  |  |  | Not Started | NA
Anonymized Table of Personnel and Work Effort |  |  |  | Not Started | NA
Redacted and Anonymized Budget and Narrative |  |  |  | Not Started | NA
2. Expertise and Resources (E&R) Not Anonymized Document
1. Table of Personnel and Work Effort |  |  |  | Not Started
2. Biographical Sketches |  |  |  | Not Started
3. Current and Pending Support |  |  |  | Not Started
4. Letters or Statements |  |  |  | Not Started
5. Facilities and Equipment |  |  |  | Not Started
6. Open Science & Data Management Plan |  |  |  | Not Started
Part 3: Separately Uploaded Files
Total Budget |  |  |  | Not Started
High-End Computing (HEC) request |  |  |  | Not Started

## Collaborator Tracking
Name | Role | Affiiliation/Dept | Email | Admin contact | Biosketch | Table of Work | Current and Pending | Letters of Support from End User Organization | Budget | Budget Justification